## Sheet1
ChessAI Project Schedule Tracking

Status	Priority	Project/Task	Description	Deliverable	Deadline	Put Back	Reason	Finish Date	Days Left	Performer
Done		GUI	Create GUI interface for human to play with machine
Done	High	Forking processes	Make it possible for Godot to fork python processes, so that Godot can use algorithms implemented in python	Engine class	26/11/21			24/12/21	-	Lâm
Done	Low	Godot-Python Mediator	Create a mediator that understand what algorithm Godot wants to use, and forward it to the appropriate engine	pychess.py	05/12/21			26/12/21	-	Lâm

Running		Implementation	Code algorithms for the chess engine
Done	High	Quiescent		Quiescent algorithm	28/11/21	01/12/21	Team members’ schedules conflict		-	Mạnh
Done	High	Null-move		Null-move algorithm	28/11/21	01/12/21	Team members’ schedules conflict		-	Vũ Minh
Dismissed	Medium	Search Trace	Print debugging information (required by Dr. Quang): / +) Moves from the current position that lead to the position the engine thinks is best / +) History of examined (closed) nodes	Algorithms tweaked with the option to print	05/12/21		Project scope misunderstanding		-	All
Done	High	Measurement Tool	Write a python script to calculate average evaluation time, per FEN per depth	TimeTester.py	04/12/21				-	All
Dismissed	Medium	Optimization	Optimize the algorithms to run faster	Enhanced Algorithm	15/12/21		Not necessary		-	All
Dismissed	High	Chess Game Wrapper	Each algorithm only consider one position at a time. / We need to check for repetitions.	Idk?	10/12/21		Not necessary, controversial			Mạnh

Running		Closeout	Prepare for presentation & submission documents
Running	Medium	Slideshow		Powerpoint Slideshow	24/12/21	08/01/22	Writing Report process delayed		9	All
Running	High	Writing Reports		Individual reports	15/12/21	01/01/22	Laziness, late feedback from project leader. / Team member’s sick (Vminh) / Vminh hasn’t finished report (29/12)		2	All
Running	High	Integrating reports		Full report	05/11/21	05/01/22	Report submission delayed		6	Lâm
Running	Medium	Submission		Completed Project	10/01/22	11/01/22			12	Lâm
Running	High	Write README file	Readme file with instructions to install packages, libs,…	README.txt	08/01/22	08/01/22	Scope creep (30/12/2021)		9	???

Running		UNTIL PRESENTATION:			11/01/22				12