## Sheet1
ChessAI Project Schedule Tracking

Status	Priority	Project/Task	Description	Deliverable	Deadline	Finish Date	Days Left	Performer
Running		GUI	Create GUI interface for human to play with machine
Done	High	Forking processes	Make it possible for Godot to fork python processes, so that Godot can use algorithms implemented in python	Engine class	26/11/21		-	Lâm
Running	Low	Godot-Python Mediator	Create a mediator that understand what algorithm Godot wants to use, and forward it to the appropriate engine	Mediator.py	05/12/21		12	Lâm

Running		Implementation	Code algorithms for the chess engine
Running	High	Quiescent		Quiescent algorithm	28/11/21		5	Mạnh
Running	High	Null-move		Null-move algorithm	28/11/21		5	Vũ Minh
Pending	Low	Search Trace	Print debugging information (required by Dr. Quang): / +) Moves from the current position that lead to the position the engine thinks is best / +) History of examined (closed) nodes	Algorithms tweaked with the option to print	05/12/21		-	All
Pending	Low	Optimization	Optimize the algorithms to run faster	Enhanced Algorithm	12/12/21		-	All

Pending		Closeout	Prepare for presentation & submission documents
Pending		Slideshow		Powerpoint Slideshow				All
Pending		Writing Reports		Individual reports				All
Pending		Integrating reports		Full report				Lâm
Pending		Submission		Completed Project				Lâm